INCIDENT OBJECTIVES (ICS 202)

| 1. Incident Name: Central City Unrest | 2. Operational Period: | Date From: 2/27/xx Time From: 1800hrs |  | Date To: 2/28/xx Time To: 0600hrs |
| --- | --- | --- | --- | --- |
| - Objective(s): - Ensure safe operations for all incident personnel by adhering to best safety practices for civil unrest and following a 2 to 1 work to rest ratio. - Provide EMS to all injured civilians in the incident area. - Provide for response to potential Hazardous Materials incidents. - Maintain the perimeter containment for the civil disobedience at: R Street on the west, 24th Street of the south, V Street om the east and 20th street on the north. - Control any fires ignited within the incident area allowing for coordination between fire and law enforcement personnel |  |  |  |  |
| 4. Operational Period Command Emphasis: The Safety of the Responders and Public is the highest Priority. Follow City arrest procedures for Offenders who do not follow the law or instructions from LE Officers. Protect Private Property and City Infrastructure from damage caused by illegal acts. |  |  |  |  |
| General Situational Awareness Temperatures and humidity will both be high during the operational period, all personnel should be sure to hydrate carefully. All personnel will ensure that they have positive communication links established between law enforcement, fire, EMS and Haz Mat personnel. All tactical activities must be coordinated between all disciplines. Maintain situational awareness of activities surrounding tactical operations. |  |  |  |  |
| 5. Site Safety Plan Required? YesLJ N Approved Site Safety Plan(s) Located at: |  |  |  |  |
| 6. Incident Action Plan (the items checked below are included in this Incident Action Plan): [&] ICS203 0 ICS207 Other Attachments: [&] ICS 204 [&] ICS 208 l8I Use of Force Policy [&] ICS 205 [&] Map/Chart □ |  |  |  |  |
| □ ICS 205A □ Weather Forecast/Tides/Currents [Z] ICS 206 |  | □□ |  |  |
| 7. Prepared by: Name: Bill Smith Position/Title: Planning Section ChilSignature: |  |  |  |  |
| 8. Approved by Incident Commander: Name: Steve Plaskett |  |  | Signature: |  |
| ICS 202 I IAP Page 1 I Date/Time: 2/26/xx 0630hrs |  |  |  |  |

ORGANIZATION ASSIGNMENT LIST (ICS 203)

1. Incident Name:	2. Operational Period: Date From: 2/27/xx	Date To: 2/28/xx

Central City Unrest	Time From: 1800	Time To: 0600

# Incident Commander(s) and Command Staff:	7. Operations Section:

IC/UCs Steve Plaskett (CCPD)		Chief Luis Lopez (CCPD) Deputy Gary Short (CCFD) Deputy Jeana Ward (CCEMS)

Deputy Rick Kent (CCFD)	Staging Area Safety Officer Paula Meche (CCPD) Michael Raney (t)		Branch

Public Info. Officer Darren Ryan (CC)	Branch Director Bill Ward (CCPD) Liaison Officer Sheila Ross		Deputy

- Agency/Organization Representatives:	Division/Group A	Matthew Lee Agency/Organization	Name	Division/Group B	 Joe Campbell

Columbia State Police George Spencer	Division/Group Perimeter Grp	Jay Chung Liberty Co. Fire Robert Blackburn	Division/Group

Liberty Co. Sheriffs Dept Joe Langston	Division/Group

# Branch

"

Branch Director Frank Watkins (CSP) Deputy

# Planning Section:

Chief Bill Smith Deputy Denise Bresino

Resources Unit Kenneth Hooks Situation Unit John Rowles

Documentation Unit Richard Terry

Demobilization Unit Lisa Miller Technical Specialists

Status Check in Recorder S. Kelly

# Logistics Section:

Chief Jim Settlemire

Division/Group Division/Group Division/Group Division/Group Division/Group

# Branch

Branch Director

Deputy Division/Group Division/Group Division/Group Division/Group Division/Group

L

M

Access Grp

Haz Mat

David Zammaron Martin Fields

Pat Sullivan

Maria Ortiz

Deputy

# Support Branch

Director Supply Unit

Facilities Unit Ground Support Unit Service Branch

Director Communications Unit

Medical Unit Food Unit

Roxanne Storm

April Horton Loren Bishop Larry Home

Charles Adams Joaquin Diaz Rusty Horton

# Air Operations Branch

Air Ops Branch Dir.  Ken Stevens Air Tactical Supervisor Benny Crawford Air Support Supervisor Robert Yeager

# Finance/Administration Section:

Chief Muchos Pesos Deputy

Time Unit Shana Anderson Procurement Unit George Henry Comp/Claims Unit  Gladys Kennedy

Cost Unit  Maria Rodriquez

- Prepared by: Name: Kenneth Hooks		Position/Title: Resources Unit Ldr	Signature:

# ICS 203

IAP Page  2

IDate/Time:  2/26/XX 1100hrs

| 1. Incident Name: Central City Unrest |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  |  | 3. I Branch: Division:A Group: Staging Area: |
| --- | --- | --- | --- | --- | --- | --- |
| 4. Operations Personnel: Name |  |  |  | Contact Number(s} |  |  |
| Operations Section Chief: Louis Lopez 530-555-5534 Branch Director: Bill Ward 530-555-5538 Division/Group Supervisor: Matthew Lee 530-555-5556 |  |  |  |  |  |  |
| 5. Resources Assigned: |  |  | (/) C 0 o w . U) ::;!: ct. | Contact (e.g., phone, pager, radio frequency, etc.) |  | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information |
| Resource Identifier | Leader |  |  |  |  |  |
| CCTF 1 | Cs 140 Sgt. Knapp |  | 1 | Radio channel 1 ph 530-555-1236 |  | DP 11900 |
|  | CCPD CC 141 |  | 2 | Radio Channel 2 ph 530-555-1244 |  | DP 11900 |
|  | CCPD CC 142 |  | 2 | Radio Channel 2 ph 530-555-1245 |  | DP 11900 |
|  | CCFD Engine 3 |  | 4 | Radio Channel 2 ph 530-555-1246 |  | DP 1 1900 |
|  | CCFE Engine 5 |  | 4 | Radio Channel 2 ph 530-555-1248 |  | DP 11900 |
| Public Order Task Force 1 O | Captain Cabrera |  | 48 | Radio Channel 1 ph 530-555-1344 |  | DP 1 1900 |
| CCTF3 | CS 103 Sgt Myers |  | 1 | Radio Channel 1 ph 530-555-1346 |  | DP 1 1900 |
| (3 LE Patrol Units) | CCPD CC 133,134,135 |  | 6 | Radio Channel 2 phone #s unknown |  | DP 1 1900 |
| CCEMS Ambulance 1 | Bailey |  | 2 | Radio Channel 2 ph 530-555-6677 |  | DP 11900 |
| CCEMS Ambulance 2 | Fisher |  | 2 | Radio Channel 2 ph 530-555-1144 |  | DP 1 1900 |
| 6. Work Assignments: Division A boundaries are R St. west, T St. east, 22nd St. north and 24th St. south. Central City TF 1 will respond to reported fires within the Division, Law Enforcement will provide security fro fire personnel. Public Order task Force 10 will patrol the Division to suppress looting and arson. Central City PD TF 3 will detain and/or transport persons taken into custody. Ambulance will provide emergency medical services throughout the Division as requested. Hazardous Materials issues should be coordinated with the Hazardous Materials Group. |  |  |  |  |  |  |
| 7. Special Instructions: Coordinate Divisions boundaries with adjoining Divisions. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. ALL PERSONNEL WILL READ AND UNDERSTAND THE "USE OF FORCE" POLICY CONTAINED IN THIS PLAN |  |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Primary Contact: indicate cell, Qager, or radio (freguency/system/channel} |  |  |  |  |  |  |
| Command jCommand/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors |  |  |  |  |  |  |
| Tac 21 Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactical Branch I |  |  |  |  |  |  |
| Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactical Branch II |  |  |  |  |  |  |
| Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |  |
| 9. Prepared by: Name: Kenneth Hooks |  |  | Positionffitle: |  | Resources Unit Ldr Signature: |  |
| ICS 204 1 tAP Page 3 |  |  | I Date/Time: 6/27/XX 1100 |  |  |  |

| 1. Incident Name: Central City Unrest |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  | 3. Branch: Division: 8 Group: Staging Area: |
| --- | --- | --- | --- | --- | --- |
| 4. Operations Personnel: Name Contact Number(s) Operations Section Chief: L=o=u=is'-L=o""'p'-=e=z'-- ....,;5:c...::3;..;:0'-'-5=-:5:c...::5:...-5=-:5=-:3::..;4'-'-_ Branch Director: B=i=ll..:.W..:...:a=r=d ,;5=3=0'-'-5=5=5'-'-5=5=3:..:::8'---_ Division/Group Supervisor: Joe Cambell 530-555-9987 |  |  |  |  |  |
| 5. Resources Assigned: |  |  | 1/) C 0 0 =1:1:: c.. | Contact (e.g., phone, pager, radio frequencv, etc.) | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information |
| Resource Identifier | Leader |  |  |  |  |
| CCTF2 | CS 150 Sgt. Nagle |  | 1 | Radio channel 1 ph 530-555-3452 | DP 1 1900 |
|  | CCPD CC 151 |  | 2 | Radio Channel 2 ph 530-555-1233 | DP 11900 |
|  | CCPDCC 122 |  | 2 | Radio Channel 2 ph 530-555-1255 | DP 1 1900 |
|  | CCFD Engine 4 |  | 4 | Radio Channel 2 ph 530-555-1266 | DP 1 1900 |
|  | CCFE Engine 6 |  | 4 | Radio Channel 2 ph 530-555-1287 | DP 1 1900 |
| Public Order Task Force 11 | CS Captain Bolles |  | 48 | Radio Channel 1 ph 530-555-1309 | DP 1 1900 |
| CC TF 3 | CS 103 Sgt Calvillo |  | 1 | Radio Channel 1 ph 530-555-1389 | DP 1 1900 |
| (3 LE Patrol Units) | CCPD CC 123,124,125 |  | 6 | Radio Channel 2 phone #s unknown | DP 1 1900 |
| CCEMS Ambulance 3 | Spencer |  | 2 | Radio Channel 2 ph 530-555-6655 | DP 1 1900 |
| CCEMS Ambulance 4 | Mission |  | 2 | Radio Channel 2 ph 530-555-1134 | DP 1 1900 |
| 6. Work Assignments: Division B boundaries are R St. west, T St. east, 20th St. north and 22nd St. south. Central City TF 2 will respond to reported fires within the Division, Law Enforcement resources will provide security to fire personnel. Public Order Task Force 11 will patrol the Division to suppress looting and arson. Central City PD TF 4 will detain and/or transport persons taken into custody. Ambulances will provide emergency medical services throughout the Division as requested. Hazardous Materials issues should be coordinated with the Hazardous Materials Group. |  |  |  |  |  |
| 7. Special Instructions: Coordinate Division boundaries with adjoining Divisions. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. ALL PERSONNEL WILL READ AND UNDERSTAND THE "USE OF FORCE" POLICY CONTAINED IN THIS PLAN |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Primary Contact: indicate cell, pager, or radio (frequency/system/channel) Command ommand/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors Tac 2J Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactics Branch I Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactics Branch II Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |
| 9. Prepared by: Name: Kenneth Hooks Position/Title: Resources Unit Ldr Signature: _ ICS 204 I tAP Page 4 I Date/Time: 6/27/XX 1100 |  |  |  |  |  |

| 1. Incident Name: Central City Unrest |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  |  |  | 3. I Branch: Division: Group: PERIMETER Grp Staging Area: |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Operations Personnel: Name |  |  |  |  |  | Contact Number(s} |  |
| Operations Section Chief: Louis Lopez Branch Director: Bill Ward Division/Group Supervisor: Ja Chung |  |  | 530-555-5534 530-555-5538 530-555-9987 |  |  |  |  |
| 5. Resources Assigned: |  |  | f/) C 0 - 0 Qf/)) :it a.. |  | Contact (e.g., phone, pager, radio freauencv, etc.) |  | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information |
| Resource Identifier | Leader |  |  |  |  |  |  |
| CCTF4 | Capt Ridley |  | 1 |  | Radio channel 1 ph 530-555-7768 |  | DP 3 1900 |
|  | CCPD CC 111 |  | 2 |  | Radio Channel 2 ph 530-555-1256 |  | DP 3 1900 |
|  | CCPD CC 112 |  | 2 |  | Radio Channel 2 ph 530-555-1290 |  | DP 3 1900 |
|  | CCPD CC 113 |  | 2 |  | Radio Channel 2 ph 530-555-1299 |  | DP 3 1900 |
|  | CCPD CC 114 |  | 2 |  | Radio Channel 2 ph 530-555-1223 |  | DP 3 1900 |
| LCo. SD | Capt Masson |  | 1 |  | Radio Channel 1 ph 530-555-1377 |  | DP 31900 |
|  | LCSO E3103 |  | 2 |  | Radio Channel 2 ph 530-555-1327 |  | DP 3 1900 |
|  | LCSO E2775 |  | 2 |  | Radio Channel 2 ph 530-555-7878 |  | DP 3 1900 |
|  | LCSO E7743 |  | 2 |  | Radio Channel 2 ph 530-555-6445 |  | DP 3 1900 |
|  | LCSO E8945 |  | 2 |  | Radio Channel 2 ph 530-555-1233 |  | DP 3 1900 |
| 6. Work Assignments: Group resources will set up controlled entry and exit points at the following locations: R Street and 21st Street, 22nd Street and 23rd Street 24th Street at S Street and T Street 20th Street at S Street All movement into and out of the incident area will be tightly controlled to authorized personnel. Maintain escape corridor for all emergency personnel, |  |  |  |  |  |  |  |
| 7. Special Instructions: Coordinate Division boundaries with adjoining Divisions. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. ALL PERSONNEL WILL READ AND UNDERSTAND THE "USE OF FORCE" POLICY CONTAINED IN THIS PLAN |  |  |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Primar:y Contact: indicate cell, 12ager, or radio (freguenc /s stem/channel) |  |  |  |  |  |  |  |
| Command jCommand/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors |  |  |  |  |  |  |  |
| Tac 2/ Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactics Branch I |  |  |  |  |  |  |  |
| Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactics Branch II |  |  |  |  |  |  |  |
| Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |  |  |
| 9. Prepared by: Name: Kenneth Hooks |  |  |  | Position/Title: Resources Unit Ldr Signature: |  |  |  |
| ICS 204 I IAP Page 5 |  |  | I Date/Time: 6/27/XX 1100 |  |  |  |  |

| 1. Incident Name: Central City Unrest |  |  |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  |  |  | 3. II Branch: ) Division: L Group: Staging Area: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ,.4 0_p_e-ra-t-io_n_s_P_e_rs_o_n_n_e_l:_N_a_m_e.. |  |  |  |  |  |  | C_o_n_ta_c_t | _N_u_m_b_e-r{-s--1 |  |
| Operations Section Chief: L;;;.;o;..;;u""is"-=Lo"'"pi;;..;ec.;;:z"'- 5::..;3:;.:0c....-..:::.5..:::.55=---=5-=5..:::.34-'--_ Branch Director: F_ra_n_k_W-at-k in-s 5'""'3..0..-5'""'5..5..-8'""'9..8.-.'-7 Division/Group Supervisor: David Zammaron 530-555-3242 |  |  |  |  |  |  |  |  |  |
| 5. Resources Assigned: |  |  |  |  | (/) C: 0 0 o.. 1 2 2 4 4 48 6 2 | Contact (e.g., phone, pager, radio frequency, etc.) Radio channel 1 ph 530-555-1211 Radio Channel 8 ph 530-555-1256 Radio Channel 8 ph 530-555-1267 Radio Channel 8 ph 530-555-1224 Radio Channel 8 ph 530-555-1225 Radio Channel 1 ph 530-555-1222 Radio Channel 1 ph 530-555-1223 Radio Channel 8 ph TBA Radio Channel 8 ph 530-555-8789 |  |  | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information DP 31900 DP 3 1900 DP 3 1900 DP 3 1900 DP 3 1900 DP 3 1900 DP 3 1900 DP 3 1900 DP 3 1900 |
| Resource Identifier CCTF5 | Leader CS 140 Cpt. Hockett |  |  |  |  |  |  |  |  |
|  |  |  | CSP P2344 |  |  |  |  |  |  |
|  |  | CSP P3356 CCFD Engine 10 CCFE Truck 10 |  |  |  |  |  |  |  |
| Public Order Task Force 13 Captain Cabrera CCPDTF 8 CS 170 Sgt. Bell (3 LE Patrol Units) CCPD CC 173, 174, 175 CCEMS Ambulance 5 La Rosa |  |  |  |  |  |  |  |  |  |
| 6. Work Assignments: Division L boundaries are T St. west, V St. east, 22nd St. south and 20th St. north CC TF 5 will respond to reported fires within the Division, Law Enforcement resources will provide security for fire pe Public Order Task Force 13 will patrol the Division to suppress looting and arson. Central City PD TF 5 will detain and/or transport persons taken into custody. Ambulance will provide emergency medical services throughout the Division as requested. Hazardous Materials issues should be coordinated with the Hazardous Materials Group. |  |  |  |  |  |  |  |  |  |
| 7. Special Instructions: Coordinate Division boundaries with adjoining Divisions. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. ALL PERSONNEL WILL READ AND UNDERSTAND THE "USE OF FORCE" POLICY CONTAINED IN THIS PLAN |  |  |  |  |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Primary Contact: indicate celL pager, or radio (frequency/system/channel) Command ,Command/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors Tac 2/ Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactics Branch I Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactics Branch II Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |  |  |  |  |
| 9. Prepared by: Name: Kenneth Hooks Position/Title: Resources Unit Ldr Signature: |  |  |  |  |  |  |  |  |  |
| ICS 204 | I IAP Page 6 |  |  |  | I Date/Time: |  | 6/27/XX 1100 |  |  |

.

| 1. Incident Name: Central City Unrest |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  | 3. II Branch: Division: M Group: Staging Area: |
| --- | --- | --- | --- | --- | --- |
| 4. Operations Personnel: Name Contact Number(s) Operations Section Chief: L=oa..au"""is'-L=o"""pa..ae=z ...;5...;3;..;;0_-5...;5...;5;...-5.;;;..5...;3;;...4;... Branch Director: F..;.ra=.n.k. -'-W ,:a=tk'""i ns=------------5=3=0..-..._5=55=-..a:8=9=8. 7 Division/Group Supervisor: Martin Fields 530-555-8242 |  |  |  |  |  |
| 5. Resources Assigned: |  |  | (/) C 0 0 :;t a. | Contact (e.g., phone, pager, radio freouencv, etc.) | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information |
| Resource Identifier | Leader |  |  |  |  |
| CCTF6 | Capt. Montgomery |  | 1 | Radio channel 1 ph 530-555-8211 | DP 1 1900 |
|  | CCPD CC 181 |  | 2 | Radio Channel 8 ph 530-555-8256 | DP 11900 |
|  | CCPD CC 182 |  | 2 | Radio Channel 8 ph 530-555-8267 | DP 11900 |
|  | CCFD Engine 6 |  | 4 | Radio Channel 8 ph 530-555-8224 | DP 11900 |
|  | CCFD Truck2 |  | 4 | Radio Channel 8 ph 530-555-8225 | DP 11900 |
| CC Public Order TF 14 | Captain Jennings |  | 24 | Radio Channel 1 ph 530-555-8222 | DP 11900 |
| CCPD TF 7 | Lt Sutter |  | 1 | Radio Channel 1 ph 530-555-8223 | DP 1 1900 |
| (3 LE Patrol Units) | CCPD CC 191, 192, 193 |  | 6 | Radio Channel 8 ph TBA | DP 11900 |
| CCEMS Ambulance 6 | Hawley |  | 2 | Radio Channel 8 ph 530-555-7789 | DP 11900 |
| 6. Work Assignments: Division M boundaries are T St. west, V St. east, and 24th St. south and 22nd St. north CC TF 6 will respond to reported fires within the Division, Law Enforcement resources will provide security for fire personnel. Public Order Task Force 14 will patrol the Division to suppress looting and arson. Central City PD TF 7 will detain and/or transport persons taken into custody. Ambulance will provide emergency medical services throughout the Division as requested. Hazardous Materials issues should be coordinated with the Hazardous Materials Group. |  |  |  |  |  |
| 7. Special Instructions: Coordinate Division boundaries with adjoining Divisions. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. ALL PERSONNEL WILL READ AND UNDERSTAND THE "USE OF FORCE" POLICY CONTAINED IN THIS PLAN |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Primary Contact: indicate cell, pager. or radio (frequency/system/channel) Command /Command/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors Tac 21 Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactics Branch I Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactics Branch II Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |
| .:9...:P..r:e.:p::a.:r.e:.d.::b:y.::..:N.;a=m-.e:.:...K:..e:n.:n:.e:t.h:.;H.:o..o.=ks===== Position/Title: Resources Unit Ldr Signature: _ ICS 204 1 tAP Page 7 I Date/Time: 6/27/XX 1100 |  |  |  |  |  |

| 1. Incident Name: Central City Unrest |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  | 3. II Branch: Division: Group: ACCESS Grp Staging Area: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Operations Personnel: Name |  |  |  | Contact Number(s) |  |  |  |  |
| Operations Section Chief: Louis Lopez 530-555-5534 Branch Director: Frank Watkins 530-555-8987 Division/Group Supervisor: Pat Sullivan 530-555-8990 |  |  |  |  |  |  |  |  |
| 5. Resources Assigned: |  |  | 1/) C: 0 - 0 Q1/)) :;t:Q. | Contact (e.g., phone, pager, radio frequency, etc.) | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information |  |  |  |
| Resource Identifier | Leader |  |  |  |  |  |  |  |
| CCTF5 | Capt. Austin |  | 1 | Radio channel 1 ph 530-555-8665 | X ST. | STAGING |  | 1900 |
|  | CCPD CC 161 |  | 2 | Radio Channel 8 ph 530-555-8655 | X ST. STAGING 1900 |  |  |  |
|  | CCPD CC 162 |  | 2 | Radio Channel 8 ph 530-555-8644 | X ST. STAGING 1900 |  |  |  |
|  | CCPD CC 163 |  | 2 | Radio Channel 8 ph 530-555-8466 | X ST. STAGING 1900 |  |  |  |
|  | CCPD CC 164 |  | 2 | Radio Channel 8 ph 530-555-8557 | X ST. STAGING 1900 |  |  |  |
| CSP Task Force 22 | Captain Owens |  | 1 | Radio Channel 1 ph 530-555-8888 | X ST. STAGING 1900 |  |  |  |
|  | CSP P2221 |  | 2 | Radio Channel 8 ph 530-555-7999 | X ST. STAGING 1900 |  |  |  |
|  | CSP P2223 |  | 2 | Radio Channel 8 ph 530-555-5432 | X ST. STAGING 1900 |  |  |  |
|  | CSP P2235 |  | 2 | Radio Channel 8 ph 530-555-7790 | X ST. STAGING 1900 |  |  |  |
|  | CSP P2238 |  | 2 | Radio Channel 8 ph 530-555-7791 | X ST. | STAGING |  | 1900 |
| 6. Work Assignments: Group resources will set up controlled entry and exit points at the following locations: V Street and 21st Street, 22nd Street, and 23rd Street 24th Street at V Street 20th Street at T Street and U Street All movement into and out of the incident area will be tightly controlled to authorize personnel. Maintain escape corridor for all emergency personnel. |  |  |  |  |  |  |  |  |
| 7. Special Instructions: Coordinate Division boundaries with adjoining Divisions. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. ALL PERSONNEL WILL READ AND UNDERSTAND THE "USE OF FORCE" POLICY CONTAINED IN THIS PLAN |  |  |  |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Primaiy Contact: indicate cell, gager, or radio {freguenc:i£IS:i£Stem/channel) |  |  |  |  |  |  |  |  |
| Command JCommand/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors |  |  |  |  |  |  |  |  |
| Tac 2/ Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactics Branch I |  |  |  |  |  |  |  |  |
| Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactics Branch II |  |  |  |  |  |  |  |  |
| Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |  |  |  |
| 9. Prepared by: Name: Kenneth Hooks |  |  | Position/Title: Resources Unit Ldr Signature: I Date/Time: 6/27/XX 1100 |  |  |  |  |  |
| ICS 204 I IAP Page 8 |  |  |  |  |  |  |  |  |

| 1. Incident Name: Central City Unrest |  | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  |  | 3. Branch: Division: Group: Haz Mat Staging Area: |  | Group |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Operations Personnel: Name |  |  |  | Contact | Number(s} |  |  |  |
| Operations Section Chief: Louis Lopez 530-555-5534 Branch Director: Division/Group Supervisor: Maria Ortiz 530-555-4242 |  |  |  |  |  |  |  |  |
| 5. Resources Assigned: |  |  | (/) C .... 0 (/) o a> '1:1: 11. | Contact (e.g., phone, pager, radio frequencv, etc.) |  | Reporting Location, Special Equipment and Supplies, Remarks, Notes, Information |  |  |
| Resource Identifier | Leader |  |  |  |  |  |  |  |
| CCFD Haz Mat 2 | Capt Wheeler |  | 6 | Radio channel 1 and 2 ph 530-555-4455 |  | Park Staging 1900 |  |  |
| CCFD Haz Mat 2 | Capt Canon |  | 6 | Radio channel 1 and 8 ph 530-555-5431 |  | Park Staging 1900 |  |  |
| 6. Work Assignments: Haz Mat Group will report directly to the Operations Section Chief and be available for response throughout the incident. Haz Mat Teams will provide Hazardous Materials response and decontamination services as required. Tactical radio frequency will be determined based upon the Division in which a Team is deployed. |  |  |  |  |  |  |  |  |
| 7. Special Instructions: If assigned to a Branch or Division, use tactics frequency of the Branch you are assigned to. Due to high temperatures and humidity, all personnel shall pay close attention to hydration. Ensure adequate communications between law enforcement, fire, EMS, Haz Mat and other resources. Non-law enforcement resources will coordinate all activities with law enforcement personnel. |  |  |  |  |  |  |  |  |
| 8. Communications (radio and/or phone contact numbers needed for this assignment): Name/Function Prima[Y Contact: indicate cell, 12ager, or radio (freguenc /s stem/channel} |  |  |  |  |  |  |  |  |
| Command ,Command/Control King Channel 1 T151.385/ R159.330 Use Tone 173.8 Command Supervisors |  |  |  |  |  |  |  |  |
| Tac 2/ Branch I King Channel 2 T151.160/ R159.225 Use Tone 151.4 Tactics Branch I |  |  |  |  |  |  |  |  |
| Tac 8/ Branch II King Channel 8 T151.310/ R159.405 Use Tone 131.8 Tactics Branch II |  |  |  |  |  |  |  |  |
| Air to Ground/ Law Enforcement King Channel 9 T/R 170.000 Air Operations. All Aircraft |  |  |  |  |  |  |  |  |
| 9. Prepared by: Name: Kenneth Hooks |  |  | Position/Title: Resources Unit Ldr Signature: I Date/Time: 6/27/XX 1100 |  |  |  |  |  |
| ICS 204 | I IAP Page 9 |  |  |  |  |  |  |  |

INCIDENT RADIO COMMUNICATIONS PLAN (ICS 205)

| 1. Incident Name: Central City Unrest |  |  |  | 2. Date/Time Prepared: Date: 2/27/XX Time: 1000 |  |  |  |  |  | 3. Operational Period: Date From: 21271XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4. Basic Radio Channel Use: |  |  |  |  |  |  |  |  |  |  |  |  |
| Zone Grp. | Ch # | Function | Channel Name/Trunked Radio System Talkgroup |  | Assignment | RX Freq Norw | RX Tone/NAG | TX Freq NorW | TX Tone/NAG |  | Mode (A, D, or M) | Remarks |
|  | 1 | Command | Channel 1 King Radios CC System |  | Command/ Control | 159.330 N |  | 151.385 N | 173.8 |  | D | Reserved for OSC, Branch Directors and Division and Group |
|  | 2 | Tactical LE/Fire | Channel 2 King Radios CC System |  | Branch I Tactical | 159.225 N |  | 151.160 N | 151.4 |  | D | All Tactical Resources on Branch I |
|  | 8 | Tactical EMS | Channel 8 King Radios CC System |  | Branch II Tactical | 159.405 N |  | 151.310 N | 131.8 |  | D | All Tactical Resources on Branch II |
|  | 9 | Air to Ground | Channel 9 King Radios CC System |  | Air to Ground | 170.000 N |  | 170.000 N |  |  | D | Reserved for Aircraft and LE Supervisors |
|  |  |  |  |  | .. |  |  |  |  |  |  |  |
| 5. Special Instructions: DO NOT USE ANY FREQUENCIES NOT SHOWN ON THE COMMUNICATION PLAN! |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Prepared by (Communications Unit Leader): Name: Cbacles Maws Signature: |  |  |  |  |  |  |  |  |  |  |  |  |
| ICS 205 I IAP Page 10 I Date/Time: 2/26/xx 1100 |  |  |  |  |  |  |  |  |  |  |  |  |

MEDICAL PLAN (ICS 206)

| 1. Incident Name: 12. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Central City Unrest Time From: 1800 Time To: 0600 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Medical Aid Stations: |  |  |  |  |  |  |  |  |  |
| Name |  | Location |  |  | Contact Number(s)/Frequency |  |  | Paramedics on Site? |  |
| Incident Aid Station #1 |  | 24th & V Street |  |  | Channel 1 Command |  |  | Yes ONo |  |
| Incident Aid Station #2 |  | 20th & R Street |  |  | Channel 1 Command |  |  | 18JYes ONo |  |
|  |  |  |  |  |  |  |  | OYes ONo |  |
|  |  |  |  |  |  |  |  | OYes ONo |  |
|  |  |  |  |  |  |  |  | OYes ONo |  |
|  |  |  |  |  |  |  |  | OYes ONo |  |
| 4. Transportation (indicate air or ground): |  |  |  |  |  |  |  |  |  |
| Ambulance Service |  | Location |  |  | Contact Number(s)/Frequency |  |  | Level of Service |  |
| Bayport Ambulance |  | Incident Aid Station #1 |  |  | Channel 1 Command |  |  | l8JALS OBLS |  |
| Fishervile Ambulance |  | Incident Aid Station #2 |  |  | ph 530-555-9111 |  |  | l8JALS 0BLS |  |
| Central City EMS |  | W & 12th Street |  |  | Channel 1 Command |  |  | 0ALS 18JBLS |  |
| Med Flight 1 |  | D Street between 31st - 34th Street |  |  | Air to Ground Channel 9 |  |  | 18JALS 0BLS |  |
| 5. Hospitals: |  |  |  |  |  |  |  |  |  |
| Hospital Name | Address, Latitude & Longitude if Helipad |  | Contact Number(s)/ Frequency | Travel Time |  |  | Trauma Center | Burn Center | Helipad |
|  |  |  |  | Air |  | Ground |  |  |  |
| Central City | D St. Between 31 & 34 St. Lat 40.0589 Lon 120.0939 |  | 374-1501 | 5 |  | 30 | 181Yes Level:-- | □181Yes No | □181Yes No |
| Faith Hospital | S &14th |  | 374-0650 | 0 |  | 30 | 181Yes Level:-- | OYes 18JNo | OYes 18JNo |
| Fisherville General | S & 1st, Fisherville |  | 452-3685 | 0 |  | 60 | l8JYes Level:-- | '8jYes No | OYes 18JNo |
| Saint Dorthy's | 3rd and River, Monroe Lat 40.0588 Lon 120.0948 |  | 374-3944 | 30 |  | 90 | l8JYes Level:-- | Yes No | Yes No |
|  |  |  |  |  |  |  | OYes Level:-- | BYes No | BYes No |
| 6. Special Medical Emergency Procedures: The DIVS/Group Supervisor will take charge of a Medical Emergency, notify Operations and Incident Communications on Command Channel. Communications will clear all radio traffic except for the emergency. The closet Incident EMT will respond to the incident for triage and treatment. The DIVS/Group Supervisor will give Communications the following information: type of injury, mechanism, type of transport needed, and locations. D Check box if aviation assets are utilized for rescue. If assets are used, coordinate with Air Operations. |  |  |  |  |  |  |  |  |  |
| 7. Prepared by (Medical Unit Leader): Name: Joaquin Diaz Signature: |  |  |  |  |  |  |  |  |  |
| 8. Approved by (Safety Officer): Name: Paula Meche Signature: |  |  |  |  |  |  |  |  |  |
| ICS 206 1 tAP Page 11 |  |  | I Date/Time: 2/27/XX 1000hrs |  |  |  |  |  |  |

SAFETY MESSAGE/PLAN (ICS 208)

| 1. Incident Name: Central City Unrest | 2. Operational Period: Date From: 2/27/XX Date To: 2/28/XX Time From: 1800 Time To: 0600 |  |
| --- | --- | --- |
| 3. Safety Message/Expanded Safety Message, Safety Plan, Site Safety Plan: February 27 Night Operational Period 1800 - 0600 Safety Issues to keep in the forefront Unstable Situation PPE!!! Warning Alarms!!! Escape Routes!!! Accountability Know where you and your crew members are at "all" times. USE LCES L Lookouts C Communications E Escape Route S Safety Zones |  |  |
| 4. Site Safety Plan Required? YesU N Approved Site Safety Plan(s) Located At: |  |  |
| s. Prepared by: Name: Paula Meche |  | Positionffitle: Safety Officer Signature: _ I Datemme: 2/27 11oo |
| ICS 208 I IAP Page 12 |  |  |